## Product Backlog
Story_Nbr | User_Story_Description | Acceptance_Criteria | Story_Points | Priority
US-01 | As a planeowner I'd like to be involved in the scheduling process for my plane. | 1. Ability to view scheduling requests for my plane. 2. Ability to approve scheduling requests 3. Ability to inquire more information from the consumer | 8 | 1
US-02 | As a planeowner I'd like to be able to edit and change availability if my plane is booked | 1. Ability to edit availability of plane | 8 | 1
US-03 | As a planeowner, I would like to be updated (email/website) on the time remaining before my plane is booked. | 1. An email is sent to the planeowner alerting them to the trip time. | 8 | 2
US-04 | As a planeowner, I would like to know the status of my plane as it's being used (start of trip/landing/returning) | 1. An email is sent to the planeowner when the trip begins. 2. An email is sent to the planeowner when the trip has ended. 3. An email is sent to the planeowner when the plane has been returned. | 21 | 2
US-05 | As a planeowner, I would like to get confirmation my plane has returned in the condition it was originally in. | 1. The owner receives a phone call or email when the plane has been returned and if the condition is in its original state. | 13 | 1
US-06 | As a planeowner, I would like to set-up cleaning / maintence if necessary. | 1. Provide the plane owner an option for cleaning and maintence of the aircraft. 2. Perhaps contract out the cleaning and maintence services to a proper business. | 13 | 2
US-07 | As a planeowner, I would like to charge the person(s) involved if my plane was returned in any condition besides what I had rented it out for. | 1. Provide the user with terms of service that includes a fee if the plane is returned with damage. 2. Provide the plane owner with terms of service in regards to property damage. 3. Provide the plane owner with an option to charge a fee if property is damaged. | 13 | 1
US-08 | As a user, I would like the ability to start a bid and be involved in the bidding process. | 1. Provide a button/option for user to open a bid on an available aircraft. | 5 | 1
US-09 | As a user, I would like to be notified if my bid was matched / outbid and propose a counter-bid within a short timeframe. | 1. Provide updates to the user if they are outbid, other users that are watching, etc. 2. Allow the user to conveniently propose a counter-bid. | 3 | 1
US-10 | As a user, I would like the ability to remove my bid | 1. Allow user to remove bid as long as the bidding has not ended. | 13 | 1
US-11 | As a user, I'd like to be able to schedule a trip through website/app/email | 1. Establish a website for the scheduling process. 2. Establish an app for the scheduling process. 3. Establish an email that users can send inquiries to schedule an aircraft. | 34 | 1
US-12 | As a user, I would like the ability to modify my trip | 1. User has ability to see their scheduled flights. 2. User has ability to modify flights. 3. User recieves confirmation of modified flight | 34 | 1
US-13 | As a user I would like to be able to check and see what planes are available | 1. User has ability to see what planes are available 2. User has ability to see what planes are available for bidding | 13 | 1
Fibonacci Series: 1,2,3,5,8,13,21,34,55,89,144,233

## Release Burndown Chart
Story Nbr | User Story Description | Story Points | Priority | Sprint
US-01 | As a planeowner I'd like to be involved in the scheduling process for my plane. | 8 | 1 | 1
US-02 | As a planeowner I'd like to be able to edit and change availability if my plane is booked | 8 | 1 | 2
US-03 | As a planeowner, I would like to be updated (email/website) on the time remaining before my plane is booked. | 8 | 2 | 2
US-04 | As a planeowner, I would like to know the status of my plane as it's being used (start of trip/landing/returning) | 21 | 2 | 2
US-05 | As a planeowner, I would like to get confirmation my plane has returned in the condition it was originally in. | 13 | 1 | 1
US-06 | As a planeowner, I would like to set-up cleaning / maintence if necessary. | 13 | 2 | 2
US-07 | As a planeowner, I would like to charge the person(s) involved if my plane was returned in any condition besides what I had rented it out for. | 13 | 1 | 2
US-08 | As a user, I would like the ability to start a bid and be involved in the bidding process. | 5 | 1 | 1
US-09 | As a user, I would like to be notified if my bid was matched / outbid and propose a counter-bid within a short timeframe. | 3 | 1 | 2
US-10 | As a user, I would like the ability to remove my bid | 13 | 1 | 3
US-11 | As a user, I'd like to be able to schedule a trip through website/app/email | 34 | 1 | 4
US-12 | As a user, I'd like the ability to modify my trip. | 34 | 1 | 1
| Total | 173
Fibonacci Series: 1,2,3,5,8,13,21,34,55,89,144,233
|  | Sprint | Remaining Work | Planned Work
|  | 1 | 173 | 60
|  | 2 | #REF! | 66
|  | 3 | #REF! | 13
|  | 4 | #REF! | 34
|  | 5 | 0 | 0

## Sprint Burndown
Story Nbr | Description | Priority | Person | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
US-01 | As a planeowner I'd like to be involved in the scheduling process for my plane. | 1 | Person 1 | 8 | 13 | 13 | 13 | 13 | 0 | 0 | 0 | 0 | 0
US-02 | As a planeowner I'd like to be able to edit and change availability if my plane is booked | 1 | Person 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | As a planeowner, I would like to be updated (email/website) on the time remaining before my plane is booked. | 1 | Person 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | As a planeowner, I would like to know the status of my plane as it's being used (start of trip/landing/returning) | 1 | Person 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | As a planeowner, I would like to get confirmation my plane has returned in the condition it was originally in. | 1 | Person 2 | 13 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0
US-06 | As a planeowner, I would like to set-up cleaning / maintence if necessary. | 1 | Person 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | As a planeowner, I would like to charge the person(s) involved if my plane was returned in any condition besides what I had rented it out for.
US-08 | As a user, I would like the ability to start a bid and be involved in the bidding process. |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5
US-09 | As a user, I would like to be notified if my bid was matched / outbid and propose a counter-bid within a short timeframe.
US-10 | As a user, I would like the ability to remove my bid |  |  | 13 | 13
|  |  | Actual | 39 | 36 | 23 | 23 | 23 | 10 | 10 | 5 | 0 | 0
|  |  | Planned | 39 | 35.1 | 31.2 | 27.3 | 23.4 | 19.5 | 15.6 | 11.7 | 7.8 | 3.9

## Daily Standup Meetings
Date | Person | What did you do today? | What is plan for Tomorrow?
Scrum Master: XX
2017-02-27 | Connor Flaherty | Planned the project. | Start working on project
2017-02-28 | Connor Flaherty | Kept planning / Balsamiq | Keep working on Balsamiq stuff / Start website
2017-03-01 | Connor Flaherty | Finished Balsamiq, framework | Work on website
2017-03-02 | Connor Flaherty | Worked on website | Assigned roles for weekend
2017-03-03 | Connor Flaherty | Finish website | Prepare for presentation